## 30-Day Video Roadmap
Day | Phase | Video Title to Record | Core Topic / What to Show | YouTube URL / Custom Value | Recording Status | GHL Workflow Status
1 | Phase 1: Setup | Welcome to Nola CRM: 3-Minute Workspace Setup | Profile completion, connecting email domain, business phone line setup | https://www.youtube.com/watch?v=YLG-cnPXdAM | Recorded | Completed
2 | Phase 1: Setup | Importing Contacts & Creating Smart Lists | Uploading CSV, mapping fields, applying tags, saving custom views | https://www.youtube.com/watch?v=p15uJVAN7JI | Recorded | Completed
3 | Phase 1: Setup | Building & Customizing Your Sales Pipelines | Creating pipeline stages, deal values, drag-and-drop opportunity cards | {{ custom_values.nola_crm_video_day3 }} | In Progress | Drafted
4 | Phase 1: Setup | Creating Custom Fields & Tagging Strategy | Adding custom contact fields (e.g., Budget, Location), tagging rules |  | Not Started | Not Started
5 | Phase 1: Setup | Connecting Calendars & Setting Availability | Integrating Google/Outlook calendars, setting meeting hours, booking links |  | Not Started | Not Started
6 | Phase 1: Setup | Connecting Social Media & Unified Conversations Inbox | Linking Facebook, Instagram, Google Business to manage all messages in one place |  | Not Started | Not Started
7 | Phase 1: Setup | Nola CRM Mobile App Setup | Downloading mobile app, enabling push notifications for instant lead alerts |  | Not Started | Not Started
8 | Phase 2: Messaging | Sending 1-on-1 Emails & SMS Messages | Navigating conversations tab, sending quick texts, attaching files |  | Not Started | Not Started
9 | Phase 2: Messaging | Creating Email & SMS Snippet Templates | Building reusable message templates with merge tags ({{contact.first_name}}) |  | Not Started | Not Started
10 | Phase 2: Messaging | Launching Bulk SMS & Email Campaigns | Sending broadcast campaigns to contact lists or tagged groups |  | Not Started | Not Started
11 | Phase 2: Messaging | Building Web Forms & Lead Capture Widgets | Creating lead forms, custom questions, embedding forms on websites |  | Not Started | Not Started
12 | Phase 2: Messaging | Installing Website Live Chat Widget | Setting up website chat widget, SMS fallback, avatar setup |  | Not Started | Not Started
13 | Phase 2: Messaging | Funnel & Landing Page Builder Overview | Creating landing pages, editing templates, adding forms/calendars |  | Not Started | Not Started
14 | Phase 2: Messaging | Automated Appointment Booking & Reminders | Setting up auto-confirmation emails and 24h/1h SMS reminders |  | Not Started | Not Started
15 | Phase 3: Automations | Workflows 101: Triggers & Actions Explained | Understanding workflow builder basics, triggers, delays, and logic |  | Not Started | Not Started
16 | Phase 3: Automations | Setting Up Missed-Call Text-Back | Auto-sending an SMS when a call is missed so you never lose a lead |  | Not Started | Not Started
17 | Phase 3: Automations | Configuring Nola AI Conversation & Booking Bot | Setting up AI auto-responder to qualify leads and book appointments |  | Not Started | Not Started
18 | Phase 3: Automations | Auto-Assigning Leads & Round-Robin Team Distribution | Routing incoming leads to specific team members automatically |  | Not Started | Not Started
19 | Phase 3: Automations | Automated Review & Reputation Requests | Sending auto SMS/Email review requests after deals reach Closed Won |  | Not Started | Not Started
20 | Phase 3: Automations | Building Multi-Step Lead Nurture Drip Sequences | Designing 7-day to 30-day automated email/SMS follow-up drips |  | Not Started | Not Started
21 | Phase 3: Automations | Webhooks, Zapier & Third-Party Integrations | Connecting external tools (Zapier, Make, Webhooks) to Nola CRM |  | Not Started | Not Started
22 | Phase 4: Scaling | Invoicing & Collecting Payments (Stripe/PayPal) | Connecting payment gateways, creating and sending custom invoices |  | Not Started | Not Started
23 | Phase 4: Scaling | Setting Up Recurring Subscriptions & Products | Creating subscription products, auto-billing, payment links |  | Not Started | Not Started
24 | Phase 4: Scaling | Tracking Ad Attribution & Lead Sources | Tracking where leads came from (Google Ads, Facebook Ads, Organic) |  | Not Started | Not Started
25 | Phase 4: Scaling | Dashboard Analytics & Revenue Reports | Reading pipeline stats, conversion rates, call/message logs |  | Not Started | Not Started
26 | Phase 4: Scaling | User Roles, Team Permissions & Security | Adding team members, setting user roles (Admin vs. User access) |  | Not Started | Not Started
27 | Phase 4: Scaling | Advanced Workflow Logic: Conditions & If/Else Branches | Branching workflows based on lead actions (replied vs. didnt reply) |  | Not Started | Not Started
28 | Phase 4: Scaling | Reputation Management & Google Business Reviews | Managing Google reviews, responding to feedback inside Nola CRM |  | Not Started | Not Started
29 | Phase 4: Scaling | Creating Affiliate & Referral Programs | Setting up referral tracking links and affiliate commission payouts |  | Not Started | Not Started
30 | Phase 4: Scaling | Full CRM Audit & Scaling Your Growth | Final checklist: reviewing active workflows, pipelines, and daily routine |  | Not Started | Not Started